## Sheet1
Tasks | Member Responsible | Start Date (MM/DD/YY) | Projected End Date (MM/DD/YY) | Progress (%)
Setup User Interface of Nightsky Webpage
HTML File | Brandon | 2017-02-27 | 2017-03-05 | 0
CSS File | Brandon | 2017-02-27 | 2017-03-05 | 0
Develop node.js server
Get node.js server to communicate with client | Brandon | 2017-03-06 | 2017-03-12 | 0
Get node.js server to communicate with Predict the Sky API | Jerry | 2017-03-13 | 2017-03-19 | 0
Get node.js server to communicate with MySQL Database | Ryan | 2017-03-13 | 2017-03-19
Develop Client-Side JavaScript
Find longitude and latitude coordinates based on given input | Jerry | 2017-03-06 | 2017-03-12 | 0
Find longitude and latitude coordinates based on geolocation | Jerry | 2017-03-06 | 2017-03-12 | 0
AJAX Call to node.js server sending long. And lat. Coordinates | Jerry | 2017-03-13 | 2017-03-19 | 0
Database Management
Fill the database according to JSON Response from API | Ryan | 2017-03-13 | 2017-03-19 | 0
Pull categories from database and create dropdown on webpage | Ryan | 2017-03-13 | 2017-03-19 | 0
Load items from category onto the webpage | Jerry | 2017-03-13 | 2017-03-19 | 0
Documentation
Interim Status Report | Brandon | 2017-03-06 | 2017-03-09 | 0
Final Presentation | Brandon | 2017-03-13 | 2017-03-20 | 0